## Slide 1: GSICS space weather subgroup meeting
Jun. 18, 2025

## Slide 2: Today’s Agenda
GRWG SWx Sub-group Membership
Brief Report on GSICS SWx SG – PRBEM joint web meeting
Work plan
Action Items
Next sub-group meeting
AOB

## Slide 3: GRWG SWx Sub-group Membership
Followings are the members of GRWG SWx Sub-group.
  CMA Cong Huang
  CU Brian Kress, Juan Rodriguez, Athanasios Boudouridis, Janet Machol
  ESA Piers Jiggens, Hugh Evans, Juha-Pekka Luntama, Melanie Heil
  EUMETSAT Andrew Monham
  KMA Eunjeong Cha, Daehyeon Oh
  NICT Tsutomu Nagatsuma (Chair)
  NOAA Christian Naylor, Jim Spann, Dimitrios Vassiliadis
  SPARC Ingmar Sandberg
  WMO Jesse Andres

## Slide 4: Brief Report on GSICS SWx SG – PRBEM joint web meeting
The joint web meeting was held in Apr. 15, 2025. Two items were discussed.
PRBEM resolution for updates of Data Analysis Procedures
  Someone on PRBEM-side should take the lead to coordinate this (TBD).
  Possible schedule
    Q3/Q4 2025 - Identify updates to be made
    Q1/Q2 2026 - Implement the changes
  There was a plan to put the data processing documentation in a folder as well which could be a way to manage changes (especially if it was written in LaTeX or markdown, etc.).
  Action: Antoine(PRBEM) to convene a PRBEM work group to work this out and see if it's agreed to do this in a dedicated Gitlab project
Use of PRBEM github for work of the GSICS Swx Sub-Group
  There is no problem on the COSPAR PRBEM side. There are 3 repos
    IRBEM - Fortran base code
    IRBEM-Extras - much more permissive
    PRBEM website - prebem.github.io
  Action - Antoine to check that PRBEM agree to have this extra project inside the PRBEM gitlab or to fit it inside the IRBEM-extras (that's under LGPL at the moment).

## Slide 5: E-mail from Antoine
Thank you for bringing this topic back to our attention. We indeed need to move forward on this issue.
This activity was briefly discussed during the IRENE workshop in Greece last month, and there was some interest from a few participants.
I guess most concerned people are in copy of these emails (if not, please forward them and notify us). I suggest we setup a telecon meeting with all interested parties to discuss the issue and see who can participate.
Regarding the time of such meeting, I see that the IRENE bi-monthly telecons happen at 12:00 UTC (0600 MDT, 0800 EDT, 2100 JST, 1400 CEST, 1500 EEST), and I suggest doing the same.
Here is a poll to chose the telecon date in the next couple of weeks: https://doonera.onera.fr/studs.php?poll=doMbtv7CDP7txNRq
Please share it with everyone who could be interested. Let's hope we can find a date before the summer to have this meeting!
On my side I've setup a demo document on Github in an editable format ([1], the generated product can be seen here [2]).
My goal is to put something like this in a PRBEM repository, so we can use it to trace the evolutions of the document. If anyone has any remark regarding this, please reach out!
Best regards,
Antoine
[1] https://github.com/AntoineBrunet/documents/blob/main/data_analysis_procedure.md?plain=1
[2] https://antoinebrunet.github.io/documents/
If you have interested in updating “Data Analysis Procedure Document”, please input your availability to Doodle ASAP.

## Slide 6: Work Plan of GSICS GRWG SWx Sub-group
Draft Work Plan was proposed by Hugh and Piers in the last meeting. If you have any questions and comments, please let us know.
Objective:
To provide coherent and consistent exchange of the data provided by radiation monitoring assets of the GSICS members.
Requirements:
Consistency of data level definitions.
Cross-calibration of datasets.
Standardisation and Specification of data, its meta data and necessary ancillary data.
Consistent data exchange service interfaces.
Tasks:
Map data level definitions of GSICS members
  The definition of data set processing levels varies from instrument to instrument. To ensure consistency for data intercomparisons, it is necessary to provide a mapping between the different levels used by the members.

## Slide 7: Work Plan of GSICS GRWG SWx Sub-group
Define procedure for dataset cross-calibration
A procedure for the cross-calibration of radiation instrument data is required. Existing procedures, such as the COSPAR/PRBEM procedure (https://prbem.github.io/documents/Standard_Data_Analysis.pdf) will be analysed. The unique aspects of the GSICS data sets on Geostationary orbits, i.e. a lack of conjunctions between spacecraft must be addressed in the process.
Identification of Ancillary Data
The datasets to be exchanged are generally time series data from in-situ radiation instrumentation, typically providing flux spectra for a set of energetic particles, e.g. protons and electrons. To effectively cross-calibrate the data additional ancillary information is required. This can include:
  Geographic location
  Magnetospheric location (B, L, L*, MLT, pitch angle), which introduces questions about consistency in the calculation method and geomagnetic field models.
  Instrument response functions
  Instrument calibration reports
Note: the COSPAR/PRBEM collaboration has developed a series of documents specifying the minimum level of ancillary data and meta-data required for a typical radiation belt data analysis, https://prbem.github.io/docs/.

## Slide 8: Work Plan of GSICS GRWG SWx Sub-group
Define Data Exchange services
To effectively share data assets between the GSICS members, a coordinated approach for dissemination is necessary. Ideally, this includes the consistent implementation of services based upon the same interfaces to both to search and deliver data, but also provision of the ancillary data in a coherent and standardized manner.
Issues to be addressed include:
  Latency in (near) real time dataset updates
  Archival access to data
  Local mirroring of data
  Standardised provision of ancillary data
  Documentation of changes in service (data outages, scheduled maintenance, recalibration/configuration of instruments, etc.)
  Technology API (HAPI servers, CDF data file directories, etc.)

## Slide 9: Assigning persons to lead individual tasks of work plan
To proceed our tasks based on the proposed work plan, following lead will be assigned. It is highly recommended that each lead will give some progress report and setting action items at the subgroup meeting.
Map data level definitions of GSICS members
  Tsutomu Nagatsuma (NICT) and TBD
Define procedure for dataset cross-calibration
  Lead: Ingmar Sandberg(SPARC) and Juan Rodriguez(CU)
Identification of Ancillary Data
  Lead: Jesse Andries(WMO) and Hugh Evans (ESA)
Define Data Exchange services
  Lead: TBD (from ESA and NOAA?)

## Slide 10: Proposal of Data Level Mapping PDS4 Processing Levels for SWx Data Sets (Draft)
Level | Definition | CMA | ESA | JAXA | KMA | NOAA | NICT | WMO
Telemetry | An encoded byte system used to transfer data from one or more instruments to temporary storage where the raw instrument data will be extracted. |  |  |  |  | L0 |  | 
Raw | Original data from an instrument. If compression, reformatting, packetization, or other translation has been applied to facilitate data transmission or storage, those processes will be reversed so that the archived data are in a PDS approved archive format. | L0 | L0 |  | L0 |  |  | L0
Partially processed | Data that have been processed beyond the raw level, but which have not yet reached calibrated status. |  | L1a | L1 |  | L1b |  | L1
Calibrated | Data converted to physical units, which makes values independent of the instrument. | L1 | L1b L2? | L2 | L1 | L2 | (L1) | L2
Derived | Results that have been distilled from one or more calibrated data products (for example, maps, gravity or magnetic fields, or ring particle size distributions). Supplementary data, such as calibration tables or tables of viewing geometry, used to interpret observational data should also be classified as ‘derived’ data if not easily matched to one of the other categories. | L2 | L2 L3 | L3 L4 | L2 |  |  | L3 L4

## Slide 11: Proposal of Data Level Mapping (cont’d)
Please review proposed data level mapping (previous page).
For cross-calibration, “Calibrated (WMO-L2)” data with ancillary data should be exchanged for producing “Derived (WMO-L3, L4)” product.

## Slide 12: Action Items
To proceed the tasks in the work plan document, the following leads (different parts, different people) needs to be assigned.
  Map data level definitions of GSICS members (1 person)
  Define Data Exchange services (2 persons)
If you have interested in updating “Data Analysis Procedure Document”, please give your availability to https://doonera.onera.fr/studs.php?poll=doMbtv7CDP7txNRq
Please review proposed data level mapping (previous page), and review which level of data should be exchanged for cross-calibration.
Proposing application produced from multiple satellite data → I propose to forward this action item to TG on the improving Data Access in CGMS/SWCG (proposed to close from GSICS GRWG).

## Slide 13: Next Meeting proposal
Next meeting: Sept. 10 (Wed.), 2025 12:00UTC-

## Slide 14: AOB?